## Implementation Checklist
Done | Task ID | Task / Scenario | Problem | Planned Solution | Technical Implementation | Expected Outcome | Priority | Status | Owner | Target Date | Notes / Evidence
☐ | T01 | Model Hosting | Qwen model runs locally; team lead should not install model/Ollama. | Host model remotely; keep model access behind FastAPI. | Containerize model service; configure OLLAMA_HOST/model endpoint; validate suitable free/demo host. | Team lead uses browser only. | High | Not Started
☐ | T02 | Public HTTPS Access | Localhost application is not accessible externally. | Expose application through HTTPS. | Serve production frontend from FastAPI; deploy/tunnel FastAPI securely. | Public browser URL works. | High | In Progress
☐ | T03 | Model Routing | Strong model for every request can increase latency/resource usage. | Classify and route requests by complexity. | Classifier → fast model for suitable requests → Qwen for complex requests; add escalation. | Efficient model usage. | High | Not Started
☐ | T04 | Schema & Business Knowledge | Model may not know correct tables, columns, relationships or terminology. | Use controlled schema and business knowledge. | Schema metadata + business dictionary + ChromaDB/RAG retrieval. | Improved SQL/business understanding. | High | In Progress
☐ | T05 | Conversation Context | Follow-ups may lose previous context. | Maintain structured session context and entity references. | Store location, role, metric, time and result references per session. | Correct follow-up interpretation. | High | Not Started
☐ | T06 | Multiple Users / Concurrency | Users may access simultaneously and contexts must not mix. | Isolate sessions and handle concurrent requests. | user_id + session_id + request_id; async FastAPI; Redis; DB pooling; limits/queue. | No cross-user context mixing. | High | Not Started
☐ | T07 | Privacy / No Chat History | Some users may not want conversations stored. | Provide normal, temporary/private and no-memory modes. | Separate active context from persistent history; define retention for cache/logs/history. | Controlled privacy behavior. | High | Not Started
☐ | T08 | Date / Timezone | Relative dates and IST/UTC boundaries can be misinterpreted. | Resolve dates deterministically. | Date/timezone resolver before SQL generation. | Correct date filtering. | High | Not Started
☐ | T09 | Business Metrics | Average, NULL, zero, historical/current balance can differ by business rule. | Define approved metric logic outside the LLM where possible. | Metric dictionary + deterministic rules + source selection. | Consistent calculations. | High | Not Started
☐ | T10 | Role / Relationship Resolution | Distributor/retailer/wholesaler/mechanic relationships can be ambiguous. | Use approved roles and relationships. | Role resolver + FK/join graph + join validation. | Correct relationships/joins. | High | Not Started
☐ | T11 | SQL Generation | LLM may generate wrong SQL. | Generate SQL using retrieved schema/business context. | Prompt/model receives controlled context; strong model generates SQL/plan. | Higher SQL accuracy. | High | In Progress
☐ | T12 | SQL AST Validation | Valid SQL syntax can still be unsafe/incorrect. | Inspect SQL before execution. | sqlglot/AST parsing; check tables, columns, joins and operations. | Unsafe/invalid SQL blocked. | High | Not Started
☐ | T13 | Security / Sensitive Data | Model could request restricted columns or operations. | Enforce security independently of LLM. | Column blacklist, permissions, read-only rules and deterministic checks. | Restricted data protected. | High | Not Started
☐ | T14 | Cost Gate | Valid queries can still be too expensive. | Control expensive queries before execution. | EXPLAIN/cost checks + thresholds; reject/request filters. | Database protected from expensive queries. | High | Not Started
☐ | T15 | Database Connection Pool | Many users can exhaust MySQL connections. | Use controlled connection pooling. | SQLAlchemy pool, limits, timeouts and health checks. | Stable DB access. | High | Completed
☐ | T16 | Schema Drift | Database changes can make AI knowledge stale. | Detect changes and refresh knowledge. | Schema Inspector/diff; invalidate affected knowledge; create new knowledge version. | No silent stale-schema usage. | High | Not Started
☐ | T17 | Network / Model Failure | Model/API/DB can fail or timeout. | Add controlled failure handling. | Timeouts, health checks, bounded retries and graceful errors. | Reliable failure behavior. | High | Not Started
☐ | T18 | Application / Model Upgrade | Updates can interrupt users or introduce regressions. | Use staged deployment and rollback. | Development → testing → staging → warm new version → gradual traffic → monitor → rollback if needed. | Safer upgrades with minimal interruption. | High | Not Started
☐ | T19 | Knowledge Versioning | New schema/business knowledge may conflict with current version. | Version and validate knowledge before activation. | knowledge_v1/v2; test retrieval and SQL scenarios before switching. | Controlled knowledge updates. | Medium | Not Started
☐ | T20 | Monitoring | Problems are difficult to diagnose without visibility. | Add operational monitoring. | Structured logs, health endpoints, latency/error metrics, model availability checks. | Better diagnosis. | Medium | Not Started
☐ | T21 | Load / Concurrent Testing | One-user success does not prove multi-user capacity. | Measure actual capacity. | Run 2/5/10+ concurrent-user tests; record latency, queue time, DB connections and errors. | Known capacity limits. | Medium | Not Started
☐ | T22 | Team Lead Demo | Team lead needs to test without installing model. | Provide browser-based test environment. | FastAPI + production frontend + accessible model + DB + HTTPS; verify externally. | Team lead can test from browser. | High | In Progress

## Progress Summary
JGH INTELLIGENCE ENGINE – IMPLEMENTATION PROGRESS
Metric | Value
Total Tasks | 22
Completed | 1
In Progress | 4
Not Started | 17
Blocked | 0
Completion % | 4.545%
Priority | Task Count
High | 19
Medium | 3
Low | 0
How to use this checklist
1. Assign an owner and target date for each task.
2. Change Status as implementation progresses.
3. Mark Done as ☑ only after the task is tested.
4. Add evidence such as commit, test result, URL, screenshot or document in Notes / Evidence.

## Scenario Tracker
Scenario | Test Question / Situation | Expected Behavior | Test Result | Status | Evidence / Notes
E1 – Relative dates | Ask a query using today/yesterday/month boundary | Correct explicit date/timezone resolution |  | Not Started
E2 – Context | Ask distributors, then 'what about retailers?' | Follow-up uses same session context |  | Not Started
E3 – Business terminology | Use an approved business synonym | Correct mapped business meaning |  | Not Started
E4 – Cost Gate | Submit an expensive join/query | Query blocked or controlled |  | Not Started
E5 – Schema drift | Change a table/column and refresh | Stale metadata detected and refreshed |  | Not Started
E6 – Sensitive data | Request restricted column | Request blocked |  | Not Started
E7 – Historical/current balance | Ask historical and current balance | Correct source/logic selected |  | Not Started
E8 – Role relationship | Ask retailer/distributor relationship query | Approved FK/join used |  | Not Started
E9 – Multiple users | Two users ask different questions simultaneously | No session/context mixing |  | Not Started
E10 – NULL/zero/average | Test approved metric edge cases | Correct business metric calculation |  | Not Started
E11 – IST/UTC | Test date near midnight boundary | Correct timezone result |  | Not Started
E12 – No history | Use private/no-memory mode | Conversation not persisted per policy |  | Not Started
E13 – Failure | Stop model/API/DB or induce timeout | Graceful error/recovery |  | Not Started
E14 – Upgrade | Deploy new version then simulate failure | New version can be rolled back |  | Not Started